## WeekMar25
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Creating the scorecard rough draft | All | 0.5 | 2018-03-23 | 100 | 2018-03-27 | 0.5
Funcitional Requirements | All | 1 | 2018-03-28 | 100 | 2018-03-28 | 1
Making the plan for next two weeks | All | 1 | 2018-03-29 | 50

## WeekApr1
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Priliminay class design
Desigining the classes needed | Group | 1 | 2018-04-06 | 100 | 2018-04-04 | 0.5
Create UML diagram | Kevin | 1 | 2018-04-06 | 100 | 2018-04-05 | 1
UI Mockup | Zach | 1.5 | 2018-04-06 | 100 | 2018-04-06
Edit project plan | Zach | 0.5 | 2018-04-06 | 100 | 2018-04-06 | 1.5
Work on resource icons | Andrew | 1 | 2018-04-13 | 40

## WeekApr8
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Create a test plan document
Work on test plan | Andrew | 2 | 2018-04-13
Update buisness model to include expanations and test cases | Andrew | 1 | 2018-04-13
Create a design alternitive analysis document
Create design alternatives | Kevin | 1.15 | 2018-04-13
Create design alternitive document | Kevin | 2 | 2018-04-13
Create source code based off current UML spec
Create PlayGame.java | Zach | 0.5 | 2018-05-01
Create Hand.java | Zach | 0.5 | 2018-05-01
Create BuildPhase.java | Zach | 1 | 2018-05-01
Create SpacePhase.java | Zach | 1 | 2018-05-01
Create Scorecard.java | Zach | 0.5 | 2018-05-01