## WeekMar25
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Creating the scorecard rough draft | All | 0.5 | 2018-03-23 | 100 | 2018-03-27 | 0.5
Funcitional Requirements | All | 1 | 2018-03-28 | 100 | 2018-03-28 | 1
Making the plan for next two weeks | All | 1 | 2018-03-29 | 50

## WeekApr1
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Priliminay class design
Desigining the classes needed | Zach | 1 | 2018-04-06 | 0
Create UML diagram | Kevin | 1 | 2018-04-06 | 0
UI Mockup | Andrew | 1.5 | 2018-04-06 | 0
Edit project plan | Zach | 0.5 | 2018-04-06 | 0

## WeekApr8
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)